## UC1
User Case - 1 | Student Interaction with AI
User case | As a student, I want to be able to interact with AI ethier by directly talking or typing and gain the feedback from AI immediately, so that I can have a more efficient way of gaining information
User Story
ID | Task | User Story | Acceptance Criteria | Priority | Estimation (story points) | Dependency
U01 | Implement functionality to send voice data to the OpenAI Assistant API and receive responses directly in Unity. | As a Student, I want to Be able to directly talk to AI about my study, so that I can have a more efficient way of gaining information. | AC1: API keys are stored securely and can be accessed by the application without exposing them in the codebase. AC2: The module can send user input to the OpenAI Assistant API and receive a response without errors. The module should handle errors gracefully and log them appropriately. AC3: Voice inputs are accurately converted to text and used as prompts for the OpenAI Assistant API. | High | 11 | None
U02 | Modify the AI feedback mechanism to handle real-time text-to-speech processing using the API's response. | As a Student, I want to Be able to listen to the feedback from AI immediately, so that I can get the answer quick and easy. | AC1: Once your project is open, there is a basic scene with a UI where users can input questions and receive responses. And a button can be pressed after the user inputs their question. AC2: Users can input voice data, which is then converted to text and displayed on the UI before being sent to the API. AC3: Text responses from the AI are converted to clear and audible speech, enhancing the interactive experience. | High | 11 | U01
U03 | Implement text input and response interface | As a Student, I want to Be able to type to the AI, so that I can have multiple ways of conversing to AI if needed. | AC1: The system provides a text input interface that supports student input for queries and receives text responses from AI, with responses displayed instantaneously. | Medium | 2 | U01
U04 | Implement mute functionality and display text responses | As a Student, I want to Be able to mute the AI but still observe the answer from AI in text, so that I can have a more convenient experience with additional options. | AC1: The system allows users to mute AI via a button, while automatically converting AI's spoken responses into text displayed on the screen. | Medium | 2 | U01
U05 | Implement conversation termination functionality | As a Student, I want to Stop the dialogue with AI, so that I can have seamless experience, stopping conversation if it gets too long/irrelevant. | AC1: The system provides a prominent "End Conversation" button that allows students to immediately terminate the conversation and clear all active dialogue records. | Medium | 2 | U01, U02

## UC2
User Case - 2 | Teacher Management of AI Agents
User case | As a teacher, I want to manage the AI agents, so that I can create and configure different AI agents for different subjects and situations.
User Story
ID | Task | User Story | Acceptance Criteria | Priority | Estimation (story points) | Dependency
U06 | Implement configuration and management functionality for multiple AI agents. | As a Teacher, I want to Be able to create AI agents, so that I can create multiple AI agents for my students. | AC1: Teachers must be able to create multiple AI agents, each with unique configurations, through an user-friendly interface. AC2: Backend functionality supports storing and retrieving AI configurations and ensures robust handling of multiple agents. | High | 3 | U13
U07 | Implement file upload and parsing functionality | As a Teacher, I want to Upload subject-related documents and prerequisite knowledge to AI agent, so that I can ensure the direction and range of the conversation. | AC1: Teachers must be able to upload documents directly through the interface. The system should provide feedback on successful uploads or any errors encountered. AC2: The system must parse the uploaded documents and integrate the content into the AI agent's knowledge base, with confirmation that the AI utilizes this information in responses. | Low | 8 | U13

## UC3
User Case - 3 | Storage of Conversation History
User case | As a student, I want to save the conversation history, so that I can view historical conversations at any time.
User Story
ID | Task | User Story | Acceptance Criteria | Priority | Estimation (story points) | Dependency
U08 | Implement saving functionality for conversation history | As a Student, I want to Save the conversation history, so that I can safely access them later (and model can learn from it). | AC1: After a conversation ends, the system automatically saves the dialogue records to the student's account. Students can view historical conversations at any time. | High | 3 | U10, U01

## UC4
User Case - 4 | Authentication and User Interface for Students
User case | As a student, I want to be able to register and login to an account, so that I can access my subject resources and start a conversation with an AI agent.
User Story
ID | Task | User Story | Acceptance Criteria | Priority | Estimation (story points) | Dependency
U09 | Implement student account registration functionality | As a Student, I want to Be able to create an account, so that I can access my subject resources. | AC1: The registration form includes fields for necessary personal information such as name, email, and password. It must validate input fields and provide clear error messages for invalid entries. AC2: The system must securely store student information in the database. | High | 2 | None
U10 | Implement student login functionality | As a Student, I want to Be able to login to an account, so that I can converse with AI. | AC1: Students must be able to log into their accounts using their email and password. Successful login redirects them to the student dashboard. | High | 1 | U09

## UC5
User Case - 5 | Authentication and User Interface for Teachers
User case | As a teacher, I want to be able to register and login to an admin account, so that I can access to the admin features and manage the AI agents securely
User Story
ID | Task | User Story | Acceptance Criteria | Priority | Estimation (story points) | Dependency
U11 | Implement account registration functionality for teachers | As a Teacher, I want to Be able to create an admin account, so that I can create different agents and perform admin tasks. | AC1: The registration form includes fields for necessary personal information such as name, email, and password. AC2: The form must include fields specific to teacher registration, including additional fields like school ID or department. AC3: The system must securely store teacher information, with additional admin privileges assigned to the account. | High | 2 | None
U12 | Implement login functionality for teacher accounts | As a Teacher, I want to Login to application as an admin, so that I can view an admin dashboard with access to things such as all available student logs, tutors, and active learning environments. | AC1: Teachers must be able to log into their admin accounts using their email and password AC2: The system verifies credentials against the database. AC3: Upon successful login, they should be redirected to the admin dashboard with appropriate privileges. | High | 1 | U11
U13 | Implement management functionalities for teacher accounts | As a Teacher, I want to Be able to add students to subjects, so that Students can access AI agents of the subjects. | AC1: Once logged in, teachers should have the ability to add new courses, manage student lists, and access all available student logs and other admin features. AC2: The Spring AI Framework must handle requests from the front-end to add, modify, or delete student accounts and link them to specific courses or subjects. | High | 3 | U12

## Sprint 2
Sprint 2 - Goal | Complete foundational tasks related to student interaction with AI, teacher account creation, and basic system functionality.
Sprint 2 - Timeframe | Week 6 - week 8 | 26/8/2024 - 16/9/2024
Sprint 2 - Workload | 22
Sprint 2 - Additional Notes | • The team will focus on user stories U01, U02, U09, U10, U11 and U12. • This sprint focuses on setting up the essential user authentication (for both students and teachers), basic student interaction with AI, and foundational functionalities. • Speech-to-Text and Text-to-Speech functions will be developed in parallel to the user account management.
Sprint 2 Backlog
ID | Sprint User Story | Subtask ID | Subtask | Corresponding AC | Assigned to | Priority | Estimation (story points) | Dependencies
U09 | As a Student, I want to Be able to create an account, so that I can access my subject resources. | U09_T1 | Design and implement the student registration and login UI in Unity | U09_AC1-2 |  | High | 1 | -
|  | U09_T2 | Implement backend logic for student account creation. | U9_AC3 |  | Medium | 1 | U09_T1
U10 | As a Student, I want to Be able to login to an account, so that I can converse with AI. | U10_T1 | Develop the login functionality for students. | U10_AC1 |  | High | 1 | U09_T2
U11 | As a Teacher, I want to Be able to create an admin account, so that I can create different agents and perform admin tasks. | U11_T1 | Design and implement the teacher registration form interface. | U11_AC1-2 |  | High | 1 | -
|  | U11_T2 | Implement backend logic for teacher account creation. | U11_AC3 |  | Medium | 1 | U11_T1
U12 | As a Teacher, I want to Login to application as an admin, so that I can view an admin dashboard with access to things such as all available student logs, tutors, and active learning environments. | U12_T1 | Develop the login functionality for teacher. | U12_AC1-3 |  | High | 1 | U11_T2
U01 | As a Student, I want to Be able to directly talk to AI about my study, so that I can have a more efficient way of gaining information. | U01_T1 | Obtain and securely store the OpenAI API keys. | U01_AC1 |  | High | 2 | -
|  | U01_T2 | Integrate OpenAI Assistant API by creating a C# script in Unity that handles HTTP requests to the OpenAI Assistant API. | U01_AC2 |  | High | 6 | U01_T1
|  | U01_T3 | Implement speech recognition to convert user voice to text using Unity-compatible libraries or services. | U01_AC3 |  | High | 3 | U01_T2
U02 | As a Student, I want to Be able to listen to the feedback from AI immediately, so that I can get the answer quick and easy. | U02_T1 | Create a basic scene with a UI and a 3D model of a person | U02_AC1 |  | High | 2 | -
|  | U02_T2 | Develop a UI in Unity that allows users to input questions and receive responses. | U02_AC1 |  | High | 3 | U02_T1
|  | U02_T3 | Implement text-to-speech functionality to vocalize the text responses from the AI. | U02_AC2-3 |  | High | 6 | U02_T2

## Sprint 3
Sprint 3 - Goal | Focus on advanced features, including AI agent management by teachers, conversation storage, and additional student interaction methods.
Sprint 3 - Timeframe | Week 9 - week 11 | 26/8/2024 - 16/9/2024
Sprint 3 - Workload | 21
Sprint 3 - Additional Notes | • The team will focus on user stories U03, U04, U05, U06, U07, U08 and U13. • This sprint is to enhance AI functionalities and expand system capabilities for teachers and advanced student interactions. • U6, U7, U13 will be developed in parallel to U3, U4 and U5.
Sprint 3 Backlog
ID | Sprint User Story | Subtask ID | Subtask | Corresponding AC | Assigned to | Priority | Estimation (story points) | Dependencies
U06 | As a Teacher, I want to Be able to create AI agents, so that I can create multiple AI agents for my students. | U06_T1 | Develop a management interface for AI agents within Unity. | U06_AC1 |  | High | 1 | -
|  | U06_T2 | Implement AI agent management backend in Spring AI Framework. | U06_AC2 |  | High | 2 | U06_T1
U07 | As a Teacher, I want to Upload subject-related documents and prerequisite knowledge to AI agent, so that I can ensure the direction and range of the conversation. | U07_T1 | Create a file upload and processing module. | U07_AC1 |  | Medium | 2 | U12_T1
|  | U07_T2 | Enhance AI understanding with uploaded content. | U07_AC2 |  | Low | 5 | U07_T1
U03 | As a Student, I want to Be able to type to the AI, so that I can have multiple ways of conversing to AI if needed. | U03_T1 | Develop text-based communication features within the Unity interface. | U03_AC1 |  | Medium | 2 | U01
U04 | As a Student, I want to Be able to mute the AI but still observe the answer from AI in text, so that I can have a more convenient experience with additional options. | U04_T1 | Implement features for muting AI and display text responses | U04_AC1 |  | Medium | 2 | U01
U05 | As a Student, I want to Stop the dialogue with AI, so that I can have seamless experience, stopping conversation if it gets too long/irrelevant. | U05_T1 | Implement features for terminating conversations. | U05_AC1 |  | Medium | 2 | U01, U02
U08 | As a Student, I want to Save the conversation history, so that I can safely access them later (and model can learn from it). | U08_T1 | Implement conversation logging systems. | U08_AC1 |  | High | 2 | U01, U10
U13 | As a Teacher, I want to Be able to add students to subjects, so that Students can access AI agents of the subjects. | U13_T1 | Develop the user interface for managing student accounts and courses | U08_AC1 |  | High | 1 | U01, U10
|  | U13_T2 | Implement backend support for student and course management in Spring AI Framework. | U08_AC2 |  | High | 2 | *U08